## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2022-swen-261-01-A AAAAAAAA
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As an admin I want to access backend product control so that I can add, remove, and update products. | Given there is data to access in the backend when I query for information then I expect to receive the data on the front end. | Pass | JC; 10/15/22 | Pass | JC; 11/6/22
| Given I am the store owner when I add products in the front end then I expect data to be changed in the backend | Pass | JC; 10/15/22 | Pass | JC; 11/6/22 User Carts tracked but not explicitly updated in json.
As a developer I want to build a backend skeleton so that other developers can implement their structures | Given I am a developer when I initeract with the skeleton then I expect backend functionality for frontend implementations | Pass | JC, DA, ZB; 10/16/22; Most functionality was complete, added some methods | Pass | JC; 11/6/22
As a customer I want to access the home page so that I can look at/buy products | Given the home link in the top dashboard when I select it then I expect to view a list of all available products. | Pass | CN; 10/19/22 | Pass | CN; 11/6/22
| Given the website's initial startup when I open my browser and enter the URL then I expect to automatically be on the home page. | Pass | CN; 10/19/22 | Pass | CN; 11/6/22
As a user I want to be able to navigate to Home, About, Cart, and Login pages so that I can use all features of the website. | Given I am a user not logged into the site WHEN I use the navigation bar, THEN I expect that I can navigate to Home, About, Cart, Search, Login from every page | Pass | ZB; 10/5/22 | Pass | ZB; 11/6/22 About has been removed from navigation
As a customer I want to login so that I can save products to my cart and checkout products. | Given no one is logged in when I log into the website then I should be logged into the website even if I switch between the sub pages of the website | Pass | CN; 10/18/22 | Pass | CN; 11/6/22 Refreshing webpage logs out user. Possibly implement session key in the future.
As a e-store owner I want to login so that I can manage the product inventory. | Given a user has no account when they attempt to log in then an account should be created for them and they should be logged in. | Pass | CN; 10/20/22 | Pass | CN; 11/6/22 Acccount is now created when signing up.
As a customer I want to have a password for my account so that only I can access my account. | Given that password and username matches when the user logs in then the user should successfully log in. | Pass | ZB; 10/19/22 | Pass | ZB; 11/6/22
| Given that password and username does not match when the user logs in then the user should not successfully log in. | Pass | ZB; 10/20/22 | Pass | ZB; 11/6/22
As a user I want to log out so that other people can't access my account. | Given a user is logged in when I log out of the website then I should be logged out of the website even if I switch between the sub pages of the website | Pass | ZB; 10/20/22 | Pass | ZB; 11/6/22
As a customer I want to be able to add products to my shopping cart so that I can manage my cart. | GIVEN there are items in my shopping cart WHEN I select remove item THEN I expect the product to be removed from my shopping cart. | Pass | CN; 10/20/22; add and remove buttons not on cart page and moved to product- page | Pass | CN; 11/6/22
As a customer I want to be able to remove products from my shopping cart so that I can manage my cart. | Given there are items in my shopping cart when I am logged out then other accounts should not be able to remove the items | Pass | CN; 10/20/22 | Pass | CN; 11/6/23
As a customer I want to checkout my shopping cart so that I can receive my product. | Given I'm on my cart page when there are items in my cart, then I should see a way to checkout | Pass | SZ; 10/20/22; | Pass | SZ; 11/6/22;
| ADDED AFTER DEMO: Given I am on my cart page when the items in my cart have been removed from inventory by an admin then I should see a message that the items have been removed from the store. | Fail | SZ; 10/20/22; No message shown | Pass | SZ; 11/6/22;
| Given I am on my cart page when the items in my cart have been removed from inventory by an admin then I expect not to be able to checkout. | Pass | SZ; 10/20/22 | Pass | SZ; 11/6/22;
| Given the items in my cart are not available in the product inventory when I checkout, then my checkout should be unsuccessful. | Pass | SZ; 10/20/22 | Pass | SZ; 11/6/22;
| ADDED AFTER DEMO: Given the items in my cart are not available in the product inventory when I checkout, then my checkout should show a message that the product is no longer available. | Fail | SZ; 10/20/22; No message shown | Pass | SZ; 11/6/22;
| Given the items in my cart are still available in the product inventory when I checkout, then my checkout should be successful | Pass | SZ; 10/20/22 | Pass | SZ; 11/6/22;
As a customer I want to be able to search products so I can look for specific products. | Given I type in characters of the desired product when products exist in the inventory then I expect them to display accordingly. | Pass | DA; 10/20/2022 | Pass | DA; 11/6/22
| Given products don't exist in the inventory when the user types their names then no products should be displayed. | Pass | DA; 10/20/2022 | Pass | DA; 11/6/22 Products that have a quantity of zero are still searchable
As a customer I want to be able to access the search page so I can look for specific products. | Given the search page link in the dashboard when I select it then the browser should navigate or display the search bar | Pass | DA; 10/20/2022 | Pass | DA; 11/6/22
| Given the home page link in the dashboard when I slect it then the search bar should disappear | Fail | DA; 10/19/2022; Search page implemented but search bar not in nav menu. Nothing Disappears | Pass | DA; 11/6/22 Search bar now displayed in nav bar and dis-appearing when not searching
As a user of STLucky I want to experience a bug-free and usable website so that I can leave with a great impression of the store. | Given I am a user When I interact with the website I expect to be satisfied with the ease of use and visual quality. |  |  | Pass | SZ; 11/6/22;
| Given an admin removes an item from the store When I am a user viewing my shopping cart I expect a message that notifies me this action has happened. |  |  | Pass | SZ; 11/6/22;
| Given a user checks out items before another user, when I checkout an item I expect a message that products in the cart are no longer available. |  |  | Pass | SZ; 11/6/22;
| Given I am an Admin, I expect to not be redirected to a forbidden page when logging in. |  |  | Pass | SZ; 11/6/22; Another error with routing occurs when logging out. It redirects you to the most recent product page instead of home.
| Given I am a user who has filled out sign-up information I expect to be signed up and to recieve a message of confirmation or failure. |  |  | Pass | SZ; 11/6/22;
| Given I am a user, when I hover over a button for 1 second, I expect to see a description of what a button does. |  |  | Pass | DA; 11/6/22 Some buttons don't have this functionality, but the most vague ones do
| Given I am a user, when I am viewing products on the homepage, I expect to be able to search for products from the same page. |  |  | Pass | DA; 11/6/22 Maybe consider having the products on the home page update along with the search in the future
| Given I am a user, When I am not logged in and viewing the cart page, I expect to see a message telling me to log in to use the shopping cart. |  |  | Pass | DA; 11/6/22
| Given I am a user trying to add an item to the cart, When I am not logged in, I expect to see a message telling me to log in to add an item to the shopping cart. |  |  | Pass | DA; 11/6/22
| Given I am a user trying to add an item to the cart, When there are not enough items in stock, then I expect to receive a message that there are no more items left. |  |  | Pass | DA; 11/6/22
| Given I am a user on a product page, When removing an item from a cart, I expect to only see the button to remove the item from the cart once the item is in the cart. |  |  | Pass | CN; 11/6/22
| Given I am an admin, When I enter data to create a product, I expect my data to be validated and show messages if data is incorrect. |  |  | Pass | CN; 11/6/22
| Given I am a user, When I view products out of stock products in the store, I expect to not see them. |  |  | Pass | CN; 11/6/22 As a User I want to view items by rating so that I can buy high quality products.
As a User I want to give ratings to products so that I can share what I think about it. | Given I am a user on the e-store when I access the product page then I should be able to see ratings of the product |  |  | Pass | CN; 11/6/22
| Given I am a customer on the e-store when I access the product page then I should be able to add a rating to the product |  |  | Pass | CN; 11/6/22
| Given I am a customer on the e-store when I access the product page then I should be able to add edit my rating of the product |  |  | Pass | JC; 11/6/22
As a customer I want to view images of the product so that I may see the product I may purchase. | Given some product when I view a preview or go to its products page then I expect to visibly view the product in 3d |  |  | Pass | JC; 11/6/22; Does not work on some browsers like opera
As a DEVELOPER I want to REORGANIZE THE BACKEND so that FRONT-END LOGIC and BACKEND INTERCONNECTIVITY CAN BE MINIMIZED. | Given I am using the website when I contact the server then the backend to send the proper response. |  |  | Pass | JC; 11/6/22
As a buyer I want to select the material of the product so that I can customize the product I'm buying. | Given I am buying a product when I enter the product page then I EXPECT to be able to customize my product with: Section Coloring, Material (Filament type), Size Expediency (Including shipping), Shipping as a gift checkbox . |  |  | Pass | JC 11/6/2022
| Given I have a product when I interact with that by buying, updating or deleting then I expect to be handling Size Expediency (Including shipping), Shipping as a gift checkbox .. |  |  | Pass | JC; 11/6/22
As a User I want to view items by rating so that I can buy high quality products. | Given I am a User, When I view products, I expect to see the products sorted in order of rating. |  |  | Pass | JC; 11/6/22

## Team C Testing
User Story | Acceptance Criterion | Team C | DC; 11/03/2022
As an admin I want to access backend product control so that I can add, remove, and update products. | Given there is data to access in the backend when I query for information then I expect to receive the data on the front end. | Pass | DG; 11/3/2022
| Given I am the store owner when I update products in the front end then I expect data to be changed in the backend | Pass | DG; 11/3/2022
| Given I am the store owner when I add products in the front end then I expect data to be changed in the backend | Pass | DG; 11/3/2022
| Given I am the store owner when I delete products in the front end then I expect data to be changed in the backend | Pass | DG; 11/3/2022
As a developer I want to build a backend skeleton so that other developers can implement their structures | Given I am a developer when I initeract with the skeleton then I expect backend functionality for frontend implementations | Fail | DC; 11/03/2022
As a customer I want to access the home page so that I can look at/buy products | Given the home link in the top dashboard when I select it then I expect to view a list of all available products. | Pass | DG; 11/3/2022
| Given the website's initial startup when I open my browser and enter the URL then I expect to automatically be on the home page. | Pass | DG; 11/3/2022
As a user I want to be able to navigate to different subpages of the website so that I can use all features of the website | Given I am a user WHEN I use the navigation bar THEN I expect that I can navigate to Home, About, Cart, Search, and logout from every page | Pass | DG; 11/3/2022
| Given I am an Admin WHEN I use the navigation bar, THEN I expect that I can navigate to Home, About, Search, Logout from every page. | Pass | DG; 11/3/2022
| Given I am a user not logged into the site WHEN I use the navigation bar, THEN I expect that I can navigate to Home, About, Cart, Search, Login from every page | Pass | DG; 11/3/2022
As a customer I want to login so that I can save products to my cart and checkout products. | Given no one is logged in when I log into the website then I should be logged into the website even if I switch between the sub pages of the website | Pass | DG; 11/3/2022
As a e-store owner I want to login so that I can manage the product inventory. | Given a user has no account when they attempt to log in then an account should be created for them and they should be logged in. | Fail | DG; 11/3/2022: The sign up button provides no feedback that the action worked
As a customer I want to have a password for my account so that only I can access my account. | Given that password and username matches when the user logs in then the user should successfully log in. | Pass | DC; 11/03/2022
| Given that password and username does not match when the user logs in then the user should not successfully log in. | Pass | DC; 11/03/2022
As a user I want to log out so that other people can't access my account. | Given a user is logged in when I log out of the website then I should be logged out of the website even if I switch between the sub pages of the website | Pass | DC; 11/03/2022
As a customer I want to be able to add products to my shopping cart so that I can manage my cart. | GIVEN there are items in my shopping cart WHEN I select remove item THEN I expect the product to be removed from my shopping cart. | Pass | DC; 11/03/2022
As a customer I want to be able to remove products from my shopping cart so that I can manage my cart. | Given there are items in my shopping cart when I am logged out then other accounts should not be able to remove the items | Pass | DC; 11/03/2022
As a customer I want to checkout my shopping cart so that I can receive my product. | Given I'm on my cart page when there are items in my cart, then I should see a way to checkout | Pass | DC; 11/03/2022
| ADDED AFTER DEMO: Given I am on my cart page when the items in my cart have been removed from inventory by an admin then I should see a message that the items have been removed from the store. | Pass | DC; 11/03/2022
| Given I am on my cart page when the items in my cart have been removed from inventory by an admin then I expect not to be able to checkout. | Pass | DC; 11/03/2022
| Given the items in my cart are not available in the product inventory when I checkout, then my checkout should be unsuccessful. | Pass | DC; 11/03/2022
| ADDED AFTER DEMO: Given the items in my cart are not available in the product inventory when I checkout, then my checkout should show a message that the product is no longer available. | Pass | DC; 11/03/2022
| Given the items in my cart are still available in the product inventory when I checkout, then my checkout should be successful | Pass | DC; 11/03/2022
As a customer I want to be able to search products so I can look for specific products. | Given I type in characters of the desired product when products exist in the inventory then I expect them to display accordingly. | Pass | DG; 11/3/2022: When text is entered that could match multiple products the search bar doesn't work
| Given products don't exist in the inventory when the user types their names then no products should be displayed. | Pass | DG; 11/3/2022
As a customer I want to be able to access the search page so I can look for specific products. | Given the search page link in the dashboard when I select it then the browser should navigate or display the search bar | Pass | DC; 11/03/2022
| Given the home page link in the dashboard when I slect it then the search bar should disappear | Pass | DC; 11/03/2022
As a user of STLucky I want to experience a bug-free and usable website so that I can leave with a great impression of the store. | Given I am a user When I interact with the website I expect to be satisfied with the ease of use and visual quality. | Fail | DG; 11/3/2022: The site is a little bare bones and asymmetric, some components look nice while others don't
| Given an admin removes an item from the store When I am a user viewing my shopping cart I expect a message that notifies me this action has happened. | Pass | DG; 11/3/2022
| Given a user checks out items before another user, when I checkout an item I expect a message that products in the cart are no longer available. | Pass | CA 11/03/2022
| Given I am an Admin, I expect to not be redirected to a forbidden page when logging in. | Pass | CA 11/03/2022
| Given I am a user who has filled out sign-up information I expect to be signed up and to recieve a message of confirmation or failure. | Fail | DG; 11/3/2022: You can only sign in as an existing user or ADMIN
| Given I am a user, when I hover over a button for 1 second, I expect to see a description of what a button does. | Fail | DG; 11/3/2022: No description given
| Given I am a user, when I am viewing products on the homepage, I expect to be able to search for products from the same page. | Fail | HC; 11/3/2022; Hitting search takes me to a new page
| Given I am a user, When I am not logged in and viewing the cart page, I expect to see a message telling me to log in to use the shopping cart. | Pass | DG; 11/3/2022
| Given I am a user trying to add an item to the cart, When I am not logged in, I expect to see a message telling me to log in to add an item to the shopping cart. | Pass | DG; 11/3/2022
| Given I am a user trying to add an item to the cart, When there are not enough items in stock, then I expect to receive a message that there are no more items left. | Pass | HC; 11/3/2022; The message informs me that I have too many items in my cart, maybe more descriptive text explaining what is going on
| Given I am a user on a product page, When removing an item from a cart, I expect to only see the button to remove the item from the cart once the item is in the cart. | Fail | HC; 11/3/2022; Should have some way to remove a product from the cart from the cart page
| Given I am an admin, When I enter data to create a product, I expect my data to be validated and show messages if data is incorrect. | Fail | HC; 11/3/2022; There was no information explaining to me that I put the wrong data type in input fields when creating an item from admin
| Given I am a user, When I view products out of stock products in the store, I expect to not see them. | Fail | HC; 11/3/2022; Item with a quantity of zero is still visible from products as a user
As a User I want to give ratings to products so that I can share what I think about it. | **Given** I am a user on the e-store **when** I access the product page **then** I should be able to see ratings of the product
**Given** I am a customer on the e-store **when** I access the product page **then** I should be able to add a rating to the product
**Given** I am a customer on the e-store **when** I access the product page **then** I should be able to add edit my rating of the product
**Given** I am a admin on the e-store **when** I access the product page **then** I should be able to manage ratings of the product
As a customer I want to view images of the product so that I may see the product I may purchase. | Given some product when I view a preview or go to its products page then I expect to visibly view the product
As a DEVELOPER I want to REORGANIZE THE BACKEND so that FRONT-END LOGIC and BACKEND INTERCONNECTIVITY CAN BE MINIMIZED. | **Given** I am using the website **when** I contact the server **then** the backend to send the proper response.
| 404 page | Fail | HC; 11/3/2022; When i change the field in the URL, no 404 page
| Persistance after refresh | Fail | HC; 11/3/2022; When I refresh the page, all data persistance (login, cart) is logged out